## Gantt Chart
BrightTV Viewership Analytics — Project Gantt Chart
Period: 09 Apr 2026 – 19 Apr 2026 ¦ Author: Student ¦ Due: 19 April 2026
Phase | Task | Owner | Start | End | 09 Apr | 10 Apr | 11 Apr | 12 Apr | 13 Apr | 14 Apr | 15 Apr | 16 Apr | 17 Apr | 18 Apr | 19 Apr
PLANNING
Planning | Define assignment scope & CEO questions | Siphamandla | 09 Apr | 09 Apr
Planning | Review case study & design project approach | Siphamandla | 09 Apr | 10 Apr
Planning | Set up Databricks, Excel & GitHub workspace | Siphamandla | 09 Apr | 10 Apr
DATA PROCESSING
Data Processing | Convert datasets and load into Databricks | Siphamandla | 10 Apr | 10 Apr
Data Processing | Clean user & viewership data | Siphamandla | 10 Apr | 11 Apr
Data Processing | Create time/date and duration calculations | Siphamandla | 11 Apr | 11 Apr
Data Processing | Build final joined dataset for analysis | Siphamandla | 11 Apr | 2026-04-12
ANALYSIS
Analysis | User & usage trends analysis | Siphamandla | 12 Apr | 2026-04-13
Analysis | Consumption factors analysis | Siphamandla | 12 Apr | 13 Apr
Analysis | Low consumption day analysis | Siphamandla | 13 Apr | 13 Apr
Analysis | Growth initiative analysis | Siphamandla | 13 Apr | 14 Apr
VISUALISATION
Visualisation | Build pivot tables in Excel | Siphamandla | 13 Apr | 14 Apr
Visualisation | Create charts & dashboards | Siphamandla | 15 Apr | 15 Apr
PRESENTATION
Presentation | Build PowerPoint slides | Siphamandla | 15 Apr | 17 Apr
Presentation | Write key insights & recommendations | Siphamandla | 15 Apr | 17 Apr
Presentation | Final review & proofreading | Siphamandla | 18 Apr | 18 Apr
SUBMISSION
Submission | Push all files to GitHub | Siphamandla | 19 Apr | 19 Apr
Submission | Final submission check | Siphamandla | 19 Apr | 19 Apr
LEGEND |  | Planning
Data Processing
Analysis
Visualisation
Presentation
Submission